## Sheet1
COM3001 Gantt Chart |  | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | B | B | B | 12 | 13 | 14 | 15 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | B | B | B | B | 8 | 9 | 10 | 11 | 12
|  | Week Beginning | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25
Deliverables | Date
Interim Discussion | Sem 1 Week 7-9 | bar: 2019-11-18 to 2019-12-02
Draft Report Submission | 2020-03-24 | bar: 2020-03-23
Implementation Demonstration | Sem 2 Week 9-10 | bar: 2020-05-04 to 2020-05-11
Final Submission | 2020-05-26 | bar: 2020-05-25
Research
Explore potential chat bot projects | bar: 2019-10-07
Research potential datasets | bar: 2019-10-14 to 2019-10-21
Explore potential applications and use cases for a chat bot | bar: 2019-10-21
Explore existing Wikipedia chatbot solutions | bar: 2019-10-28
Explore DBPedia dataset and implementations | bar: 2019-11-04
Write up literature review | bar: 2019-11-04 to 2019-11-18
Design
Identify measurable requirements | bar: 2019-11-25
Create design diagrams for system | bar: 2019-12-02 to 2019-12-09
Create conversation flow diagrams | bar: 2019-12-09
Data design | bar: 2019-12-16
User interface design | bar: 2019-12-23
Create test plan | bar: 2019-12-30
Implementation | bar: 2020-01-06
Initialise project and required libraries | bar: 2020-01-06
Implement user input and control | bar: 2020-01-13 to 2020-01-20
Implement DBPedia integration | bar: 2020-01-27 to 2020-02-03
Implement NLP for user queries | bar: 2020-02-03
Implement chat bot responses based on query | bar: 2020-02-10
Create user interface | bar: 2020-02-17 to 2020-02-24
Implement ML to adjust to user feedback on incorrect response
Testing | bar: 2020-03-02 to 2020-03-09
Test system against test plan | bar: 2020-03-16 to 2020-03-23
Run user acceptance testing with testers
Analysis | bar: 2020-03-30
Evaluate project against aims and objectives | bar: 2020-04-06
Analyse testing data | bar: 2020-04-06
Identify areas of improvement
Write-up
Complete write-up for implementation,testing,analysis | bar: 2020-04-13 to 2020-05-18